## Data analyst Project schedule
Phase | Date (Day) | Task | Primary Tool | Deliverable
Phase 1: Project Scoping & Definition
| 2025-10-07 | Sign NDA & Project Charter Finalization. | Document/Meeting | Signed NDA (Non-Disclosure Agreement) and Final Project Charter document.
| 2025-10-08 | Initial Data Discovery and Data Dictionary creation. | Excel/Python | Draft Data Dictionary (includes column names, data types, and brief descriptions).
| 2025-10-09 | Architecture Diagram creation. | Drawing/Diagramming Tool | Architecture Diagram (visualizing data flow from source to final dashboard).
| 2025-10-10 | Basic Data Cleaning (Initial review and quick fixes). | Excel | Excel sheet with basic clean-up applied and a list of identified data issues.
Phase 2: Deep Cleaning & Preprocessing
| 2025-10-11 | Data Preprocessing (Missing values, duplicates, and structural errors). | Python (Pandas) | Python Script 1 (Handles initial cleaning steps).
| 2025-10-12 | Data Preprocessing (Type conversion, feature engineering, and outlier handling). | Python (Pandas) | Python Script 2 (Advanced transformations).
| 2025-10-13 | Documentation of Data Preprocessing. | Document/Notebook | Final Data Preprocessing Documentation (Jupyter Notebook or detailed ReadMe).
Phase 3: Exploratory Data Analysis (EDA)
| 2025-10-14 | EDA (Univariate Analysis and Summary Statistics). | Python (Pandas/Seaborn) | Jupyter Notebook 1 (Initial analysis, key metric tables).
| 2025-10-15 | EDA (Bivariate/Multivariate Analysis and Relationship Visualization). | Python (Seaborn/Matplotlib) | Jupyter Notebook 2 (Correlation matrices, scatter plots).
| 2025-10-16 | Documentation of EDA Findings. | Document/Report | EDA Summary Report (Highlights key trends, anomalies, and insights from analysis).
Phase 4: SQL Analysis & Modeling
| 2025-10-17 | SQL Data Cleaning and Initial Exploration. | SQL | SQL Script for Cleaning and Validation Queries.
| 2025-10-18 | SQL EDA and Complex Query Development. | SQL | SQL Script for Exploratory Queries (Grouping, window functions, etc.).
18 or 19 | 18/19 | PowerBI Discussion on Dashboard Requirements. | Meeting | Dashboard Requirements Document (Defines key visualizations and user needs).
| 19 | Top 20 SQL Queries Finalization. | SQL | Document containing the Top 20 Project SQL Queries for reporting/metrics.
| 20 | Documentation of SQL & Final Pre-Dashboard Prep. | Document/Code | SQL Documentation (Query explanations) and Clean Final Dataset output (CSV/Parquet).
Phase 5: Visualization & Delivery
20 onward | 2025-10-20 | Power BI Dashboard Development (Start Work). | Power BI | Power BI Dashboard Development in Progress.